## Instructions
BLOCKED ITEMS TRACKER — INSTRUCTIONS
v2.0 Program • Owner: PM • Log blockers within 24 hours of identification regardless of source
PURPOSE & WORKFLOW
PURPOSE | Single consolidated view of everything actively blocking program work. Blockers surface from many sources — COSMOS, ClickUp, standups, emails, tag-ups — but must be logged here to be visible, owned, and tracked to resolution.
WHO LOGS | Domain leads log blockers from their branch. PM logs anything cross-branch or surfaced in meetings. No blocker should exist for more than 24 hours before appearing here.
UPDATE CADENCE | Reviewed at every weekly tag-up. Status and days open auto-calculate. Any blocker open >5 business days (internal) or any duration (external) is a standing tag-up agenda item.
WHAT GOES HERE | Only true blockers — work that cannot proceed until a specific decision is made or action is taken. Dependencies with known timelines and risks belong in the risk register, not here.
RESOLUTION | When a blocker is resolved, set Status = Resolved and enter the Date Resolved. The item remains visible for 30 days then can be archived. Never delete resolved blockers.
BLOCKER TYPE DEFINITIONS
BLOCKER TYPE | DEFINITION | ESCALATION IMPLICATION
Internal | Blocked by something within the contractor team's control. A technical decision, a resource constraint, a dependency between team members. | Resolve within 5 business days. If not resolved, escalate to PM. Does not surface in government customer reports unless it impacts a milestone.
External — Government | Blocked by a required government decision, approval, access grant, or action. The government customer must act to unblock this. | Surface in weekly status report immediately. Log in government-facing decision authority section. Track days awaiting government action.
External — Procurement | Blocked by a pending procurement action — a mod, a PO, a GFE delivery, a license approval. | Surface to Contracts Lead immediately. If it impacts a milestone, escalate to government customer. Log related Change Request if applicable.
External — Third Party | Blocked by a vendor, subcontractor, or external dependency outside both contractor and government control. | PM owns tracking and escalation path. If subcontractor is the blocker, reference their Vendor ID and check agreement terms for remedies.
SOURCE FIELD — WHERE BLOCKERS COME FROM
SOURCE VALUE | WHEN TO USE
ClickUp | Blocker identified from a ClickUp task status or comment.
COSMOS | Blocker identified from a COSMOS task, sprint item, or status flag.
Standup | Blocker surfaced verbally in a daily standup.
Tag-up | Blocker surfaced in a weekly tag-up or branch review.
Email | Blocker identified from an email thread.
Teams/Slack | Blocker identified from a Teams or Slack message.
PM Identified | PM identified the blocker through their own review or analysis.
Other | Any other source — describe in the Notes field.

## Blocked Items Log
BLOCKED ITEMS LOG [Table: BlockedItems]
Log blockers within 24 hours • Internal blockers: resolve in 5 days or escalate • External blockers: surface in weekly report immediately • Green template row = copy for new entry
Blocker ID | Date Identified | Branch | Source | Blocker Type | Blocker Title | Full Description (what is blocked and why) | What Unblocks This | Decision Authority | Identified By | Blocker Owner | Related Task / Ref | Related Risk ID | Escalate to Customer? | Customer Notified Date | Target Resolution | Status | Date Resolved | Days Open | Notes
Format: BL-001 | MM/DD/ YYYY | Branch 1.0–6.0 | ClickUp / COSMOS / Standup etc. | Internal / External—Govt / External—Proc / External—3P | ≤10 words | Specific — what work cannot proceed | Specific action or decision needed | Who can unblock this | Name of person who found it | Name — one person only | ClickUp ID / COSMOS ref / email thread | R-001 or blank | Yes / No | MM/DD/YYYY or blank | MM/DD/ YYYY | Open / In Progress / Resolved / Escalated | MM/DD/YYYY when resolved | AUTO → formula | Context / update notes
▶ COPY THIS ROW — fill in all non-AUTO fields |  | [Branch] | [Source] | Internal | [Blocker title — what is blocked] | [Describe what work cannot proceed and the specific reason it is blocked] | [What specific decision or action resolves this] | [Name / role of person who can unblock] | [Who identified] | [Owner — one person] | [Task ref or blank] | [R-001 or blank] | No |  |  | Open |  |  | [Notes]
BL-001 | 06/01/2026 | 3.0 Security & Compliance | Tag-up | External — Government | ATO Interim Authorization Decision Pending | Security team cannot finalize RMF package submission without government AO decision on whether to pursue interim ATO or full ATO. Both paths have different documentation requirements. | Government AO to decide: interim ATO vs. full ATO path by 06/30/2026. | Government Authorizing Official (AO) | Security Lead | PM |  | R-001 | Yes | 06/05/2026 | 06/30/2026 | Escalated |  | 23 | Escalated to COR 06/05. Awaiting AO response.
BL-002 | 06/10/2026 | 4.0 Infra & Environment | Email | External — Procurement | GFE Server Delivery Delayed | Production environment configuration cannot begin until GFE servers are delivered. Government procurement tracking shows 6-week delay from original delivery date. | Government COR to provide updated GFE delivery date and authorize interim cloud workaround if delay exceeds 4 weeks. | Government COR | Infra Lead | Infra Lead |  | R-003 | Yes | 06/12/2026 | 07/15/2026 | Open |  | 14 | COR notified 06/12. Interim cloud option scoped by Infra Lead — awaiting authorization.
BL-003 | 06/15/2026 | 2.0 Software Development | COSMOS | Internal | API Schema Decision Blocking Sprint 4 Features | Three Sprint 4 features depend on a finalized API schema. Tech lead and PM have not reached agreement on versioning approach. Dev team blocked from starting feature development. | Tech lead and PM to decide API versioning approach in next sprint planning session. | Tech Lead + PM | Dev Lead | Tech Lead | COSMOS-0042 |  | No |  | 06/20/2026 | In Progress |  | 9 | Decision session scheduled 06/18. Draft schema options prepared by tech lead.
BL-004 | 06/18/2026 | 2.0 Software Development | Standup | External — Third Party | DataBridge (V-005) SME Unavailable | DataBridge Consulting SME scheduled for API integration work is unavailable due to personal emergency. No substitute resource identified. Integration work paused. | DataBridge to provide substitute SME or revised availability date within 5 business days per SUBK-003 terms. | PM — escalate to DataBridge PM per contract terms | Dev Lead | PM | SUBK-003 | R-004 | No |  | 06/25/2026 | Open |  | 6 | Formal notice sent to DataBridge 06/18 per contract notification requirements.
BL-005 | 06/05/2026 | 1.0 Program Management | ClickUp | Internal | RACI Not Finalized — Blocking Branch Reporting | RACI matrix for branches 3.0 and 4.0 not yet agreed. Domain leads unclear on accountability boundaries. Affecting quality of weekly tag-up reporting from those branches. | PM to facilitate RACI finalization session with Security Lead and Infra Lead. | PM | PM | PM |  |  | No |  | 06/12/2026 | Resolved | 06/11/2026 | 6 | RACI finalized in working session 06/11. Distributed to team.
Formulas:
Days Open = IF([Date Identified]="","",IF([Date Resolved]<>"",[Date Resolved]-[Date Identified],TODAY()-[Date Identified]))

## Summary View
BLOCKED ITEMS — SUMMARY VIEW
Auto-calculated from Blocked Items Log • Use this view for tag-up agenda and weekly status report
OPEN BLOCKERS BY STATUS
Status | Count | External (Govt/Proc/3P) | Internal | Avg Days Open | Action
Escalated | 1 | 1 | 0 | 23 | Immediate PM attention required
Open | 3 | 2 | 1 | 10 | Review at tag-up — assign resolution action
In Progress | 1 | 0 | 1 | 9 | Confirm owner has clear path to resolution
Resolved | 1 | 0 | 1 | 6 | No action — log complete
OPEN BLOCKERS BY BRANCH
Branch | Total Open | External | Escalated | Oldest Open (days)
1.0 Program Management | 0 | 0 | 0 | 0
2.0 Software Development | 2 | 1 | 0 | 0
3.0 Security & Compliance | 1 | 1 | 1 | 0
4.0 Infra & Environment | 1 | 1 | 0 | 0
5.0 OT&E | 0 | 0 | 0 | 0
6.0 Fielding & Transition | 0 | 0 | 0 | 0
ESCALATED TO CUSTOMER — REQUIRES GOVERNMENT ACTION
Blocker ID | Branch | Title | Days Open | Target Resolution | Status
▶ COPY THIS ROW — fill in all non-AUTO fields
BL-001
BL-002
BL-003