## Instructions
RISK REGISTER — INSTRUCTIONS & FIELD DEFINITIONS
v2.0 Program • Program Management Branch
FIELD | DEFINITION | ACCEPTED VALUES / GUIDANCE
Risk ID | Unique identifier. Format: R-XXX (e.g., R-001). Never reuse an ID. | R-001, R-002 …
Date Identified | Date the risk was first surfaced. | MM/DD/YYYY
Branch | Functional branch where the risk originates. | 1.0 Program Mgmt / 2.0 Software Dev / 3.0 Security & Compliance / 4.0 Infra & Environment / 5.0 OT&E / 6.0 Fielding & Transition
Risk Title | Short descriptive title (≤10 words). | Free text
Risk Description | Full narrative of the risk condition and its potential consequence. | Free text — be specific about trigger and impact
Category | Risk type classification. | Schedule / Cost / Technical / Security / Resource / Compliance / External
Likelihood | Probability the risk materializes. Assign 1–5. | 1=Rare 2=Unlikely 3=Possible 4=Likely 5=Almost Certain
Impact | Severity of consequence if the risk occurs. Assign 1–5. | 1=Negligible 2=Minor 3=Moderate 4=Major 5=Critical
Risk Score | Likelihood × Impact. Calculated automatically. | 1–25 (formula-driven)
Risk Level | Derived rating band. | Low (1–4) / Medium (5–9) / High (10–16) / Critical (17–25)
Risk Owner | Individual accountable for monitoring and mitigation. | Full name — one person, not a team
Mitigation Strategy | Actions being taken to reduce likelihood or impact. | Free text — be specific and actionable
Contingency Plan | What we do if the risk materializes despite mitigation. | Free text
Target Resolution | Date by which mitigation should be complete or risk retired. | MM/DD/YYYY
Status | Current disposition of the risk. | Open / Monitoring / Mitigated / Closed / Escalated
Trend | Direction of risk over the past reporting period. | ↑ Increasing / → Stable / ↓ Decreasing
Escalate to Customer | Does this risk require government customer visibility or decision? | Yes / No
Last Updated | Date this row was last reviewed or modified. | MM/DD/YYYY
Notes | Any additional context, decisions made, or links to related items. | Free text

## Risk Register
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20
PROGRAM RISK REGISTER
v2.0 Program • Owner: Program Management • Update cadence: Weekly tag-up
Risk ID | Date Identified | Branch | Risk Title | Risk Description | Category | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Risk Owner | Mitigation Strategy | Contingency Plan | Target Resolution | Status | Trend | Escalate to Customer | Last Updated | Notes
R-001 | 06/23/2026 | 3.0 Security & Compliance | ATO Timeline Slip | RMF package submission may be delayed due to incomplete STIG remediation, potentially blocking deployment at phase gate. | Security | 4 | 5 | 20 | Critical | Security Lead | Accelerate STIG remediation sprint; prioritize findings that block ATO submission. | Request interim ATO or phased authorization from government AO. | 09/01/2026 | Open | ↑ Increasing | Yes | 06/23/2026 | Escalated to PM. Weekly check-in with Security lead.
R-002 | 06/23/2026 | 2.0 Software Development | Technical Debt Accumulation | Rapid feature development pace is generating technical debt that may degrade code quality and increase defect rate in later sprints. | Technical | 3 | 3 | 9 | Medium | Dev Lead | Allocate 20% of each sprint to debt reduction. Track in technical debt register. | Descope lower-priority features in PI planning to create remediation sprint. | 10/01/2026 | Monitoring | → Stable | No | 06/23/2026 | Debt register reviewed bi-weekly.
R-003 | 06/23/2026 | 4.0 Infra & Environment | GFE Procurement Delay | Government-furnished equipment required for production environment has not been procured, risking dev/prod parity and deployment readiness. | External | 3 | 4 | 12 | High | Infra Lead | Coordinate with government COR on procurement timeline. Identify interim cloud environment to maintain dev continuity. | Extend dev environment timeline; adjust phase gate date if GFE not available. | 08/15/2026 | Open | → Stable | Yes | 06/23/2026 | COR notified 06/15. Awaiting procurement status.
R-004 | 06/23/2026 | 1.0 Program Management | Key Personnel Departure | Loss of a 1099 SME with deep system knowledge could create a capability gap and slow development velocity. | Resource | 2 | 4 | 8 | Medium | PM | Document institutional knowledge. Cross-train team members. Include knowledge transfer in sprint definitions. | Activate bench resource. Extend timeline for affected features. | Ongoing | Monitoring | → Stable | No | 06/23/2026 | Knowledge transfer sessions scheduled monthly.
R-005 | 06/23/2026 | 5.0 OT&E | GAT Entry Criteria Not Met | Software increments may fail to meet government acceptance testing entry criteria, requiring rework and delaying OT&E schedule. | Schedule | 3 | 4 | 12 | High | OT&E Lead | Define and enforce Dev T&E entry criteria that mirror GAT requirements. No release without internal sign-off. | Negotiate limited re-test window with government. Descope to stable feature set. | Continuous | Open | → Stable | Yes | 06/23/2026 | Entry criteria document under development.

## Summary Dashboard
RISK SUMMARY DASHBOARD
Auto-calculated from Risk Register tab • Do not edit this sheet directly
OPEN RISKS BY LEVEL
Risk Level | Count | % of Total | Threshold | Status
Critical | 1 | 20% | 0 | OK
High | 2 | 40% | 3 | OK
Medium | 2 | 40% | 8 | OK
Low | 0 | 0% | — | —
Total Open | 5 | 100% | — | —
OPEN RISKS BY BRANCH
Branch | Open Risks | Critical/High | Escalated to Customer
1.0 Program Management | 1 | 0 | 0
2.0 Software Development | 1 | 0 | 0
3.0 Security & Compliance | 1 | 1 | 1
4.0 Infra & Environment | 1 | 1 | 1
5.0 OT&E | 1 | 1 | 1
6.0 Fielding & Transition | 0 | 0 | 0