## 📋 Instructions
XXX - CONTRACT BURN RATE TRACKER
PoP: 24 Feb 2025 – 23 Feb 2026 ¦ Prime: xxxxxx
WORKBOOK STRUCTURE
⚙️ Setup | Enter contract metadata, CLIN ceiling & funded values. This is the master reference for all other sheets.
📝 Mod Tracker | Log every contract modification (P00001, P00002…). Each mod updates ceiling/funding and the history is preserved.
📅 Monthly Tabs | 13 monthly tabs (Feb partial → Feb partial). Enter Prime Actuals, Sub Actuals, and Forecast per CLIN each month.
📊 Burn Summary | Auto-calculated YTD roll-up: KPI banner, monthly table, CLIN-level summary, status flags, % burned.
📈 CLIN Charts | One burn chart per CLIN showing Ceiling, Funding, Actuals, and Actuals+Forecast projected to contract end.
COLOR LEGEND
Blue text / blue bg | Input cell — enter your data here
Black text / gray bg | Formula / auto-calculated — do not overwrite
Green text | Cross-sheet link — auto-populated from another tab
Yellow background | Key assumption — review before use
⚠️ NEAR LIMIT (red) | Cumulative burn ≥ 95% of funded amount
🟡 CAUTION (amber) | Cumulative burn ≥ 80% of funded amount
✅ ON TRACK (green) | Cumulative burn < 80% of funded amount

## ⚙️ Setup
CONTRACT SETUP & CLIN MASTER
CONTRACT METADATA
Contract Number
Program
Prime
Primary Client
Secondary Client
PoP Start
PoP End
PM
CLIN MASTER — CURRENT VALUES (Updated by Mod Tracker)
CLIN | Description | Type | Current Ceiling ($) | Current Funded ($) | Sub? | Notes
1005 | Project Management | FFP | 593717.36 | 432918.91 | No
1006 | Software Maintenance | CPFF | 727970.79 | 561144.15 | No
1007 | Software Development | CPFF | 869923.61 | 670566.12 | No
1008 | O&M | CPFF | 688014.82 | 501677.47 | No
1009 | Tier 3 Helpdesk | FFP | 33772.5 | 24625.78 | No
1010 | Training | FFP | 199225.6 | 145268.67 | No
1016 | NTIA | FFP | 268485.99 | 268485.99 | No
1017 | Other Direct Costs | COST | 132000 | 60486.24 | No
1018 | Travel | COST | 10144 | 4999.99 | No
TOTAL |  |  | 3523254.67 | 2670173.32

## 📝 Mod Tracker
📝 CONTRACT MODIFICATION TRACKER — PRIME
FROM BY TO format: enter FROM (prior value) and BY (change delta). TO = FROM + BY (auto-calculated). FROM auto-fills from prior MOD's TO. MOD TYPES: Funding ▪ Scope ▪ Admin ▪ Clause/Language ▪ Mixed
FROM BY TO LOGIC: "This MOD is increased FROM $500,000 BY $100,000 TO $600,000" ¦ FROM auto-populates from prior MOD's TO · BY = your delta input (blue) · TO = FROM + BY (auto)
Modification Details |  |  |  |  | CLIN 1005 — Proj. Mgmt (FFP) |  |  | CLIN 1006 — SW Maint. (CPFF) |  |  | CLIN 1007 — SW Dev. (CPFF) |  |  | CLIN 1008 — O&M (CPFF) |  |  | CLIN 1009 — Tier 3 Help (FFP) |  |  | CLIN 1010 — Training (FFP) |  |  | CLIN 1016 — NTIA (FFP) |  |  | CLIN 1017 — ODCs (COST) |  |  | CLIN 1018 — Travel (COST) |  |  | CLIN 1018 — Travel (COST) |  |  | CONTRACT TOTAL (All CLINs)
MOD # | Eff. Date | MOD Type | Description / What This MOD Changes | Row | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($) | FROM ($) | BY ($) | TO ($)
AWARD (Baseline) |  |  | Contract award — original baseline values. Enter award ceiling and funding amounts. | CEILING | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0
|  |  |  | FUNDING | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0
P00001 |  |  |  | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00002 |  |  |  | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00003 |  |  |  | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00004 |  |  |  | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00005 |  |  |  | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00006 |  |  |  | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00007 |  | Mixed | • Incorporate DFARS 252.204-7021 • Incorporate revised PWS (Removal of v5 vs v6 nomenclature) • Provide BY funding in amount of $153,073.42 | CEILING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | FUNDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00008 |  | Mixed | • Realign ceiling and funding for BY CLIN 0017 & 0018 • Incorporate revisied 6.10 - Training PWS • Exercise OY1 • Provide OY1 funding | CEILING |  | 593717.36 | 593717.36 | 0 | 727970.79 | 727970.79 | 0 | 869923.61 | 869923.61 | 0 | 688014.82 | 688014.82 | 0 | 33772.5 | 33772.5 | 0 | 199225.6 | 199225.6 | 0 | 268485.99 | 268485.99 | 0 | 132000 | 132000 | 0 | 10144 | 10144 | 0 | 10144 | 10144 | 0 | 3523254.67 | 3523254.67
|  |  |  | FUNDING | 0 | 98952.89 | 98952.89 | 0 | 151660.58 | 151660.58 | 0 | 181234.09 | 181234.09 | 0 | 114669.14 | 114669.14 | 0 | 5628.75 | 5628.75 | 0 | 33204.27 | 33204.27 | 0 | 268485.99 | 268485.99 | 0 | 22000 | 22000 | 0 | 1690.66 | 1690.66 | 0 | 1690.66 | 1690.66 | 0 | 877526.37 | 877526.37
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00009 |  | Mixed | • Provide incremental funding of $1,792,646.95 • Update DFARS 252.232-7007 Limitation of Government Obligation | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 98952.89 | 333966.02 | 432918.91 | 151660.58 | 409483.57 | 561144.15 | 181234.09 | 489332.03 | 670566.12 | 114669.14 | 387008.33 | 501677.47 | 5628.75 | 18997.03 | 24625.78 | 33204.27 | 112064.4 | 145268.67 | 268485.99 | 0 | 268485.99 | 22000 | 38486.24 | 60486.24 | 1690.66 | 3309.33 | 4999.99 | 1690.66 | 3309.33 | 4999.99 | 877526.37 | 1792646.95 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00010 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00011 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00012 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00013 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00014 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00015 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00016 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00017 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00018 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00019 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00020 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00021 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00022 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00023 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00024 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
P00025 |  |  |  | CEILING | 593717.36 | 0 | 593717.36 | 727970.79 | 0 | 727970.79 | 869923.61 | 0 | 869923.61 | 688014.82 | 0 | 688014.82 | 33772.5 | 0 | 33772.5 | 199225.6 | 0 | 199225.6 | 268485.99 | 0 | 268485.99 | 132000 | 0 | 132000 | 10144 | 0 | 10144 | 10144 | 0 | 10144 | 3523254.67 | 0 | 3523254.67
|  |  |  | FUNDING | 432918.91 | 0 | 432918.91 | 561144.15 | 0 | 561144.15 | 670566.12 | 0 | 670566.12 | 501677.47 | 0 | 501677.47 | 24625.78 | 0 | 24625.78 | 145268.67 | 0 | 145268.67 | 268485.99 | 0 | 268485.99 | 60486.24 | 0 | 60486.24 | 4999.99 | 0 | 4999.99 | 4999.99 | 0 | 4999.99 | 2670173.32 | 0 | 2670173.32
📋 MOD SNAPSHOT — What does this modification do? (enter description: funding increase, scope change, new clause, administrative, etc.)
CURRENT CONTRACT VALUE (Award + All Modifications) |  |  |  | CEILING | CURRENT → |  | 593717.36 | CURRENT → |  | 727970.79 | CURRENT → |  | 869923.61 | CURRENT → |  | 688014.82 | CURRENT → |  | 33772.5 | CURRENT → |  | 199225.6 | CURRENT → |  | 268485.99 | CURRENT → |  | 132000 | CURRENT → |  | 10144 | CURRENT → |  | 10144 | CURRENT → |  | 3523254.67
|  |  |  | FUNDING | CURRENT → |  | 432918.91 | CURRENT → |  | 561144.15 | CURRENT → |  | 670566.12 | CURRENT → |  | 501677.47 | CURRENT → |  | 24625.78 | CURRENT → |  | 145268.67 | CURRENT → |  | 268485.99 | CURRENT → |  | 60486.24 | CURRENT → |  | 4999.99 | CURRENT → |  | 4999.99 | CURRENT → |  | 2670173.32

## 💼 Labor Forecast
💼 LABOR FORECAST — CPFF CLINs 1006 ¦ 1007 ¦ 1008
Enter hours in BLUE cells. Cost = Hours × Burdened Rate × 1.08 (CPFF fee). CPFF CLIN Forecast cells in monthly burn tabs auto-populate from this sheet.
CPFF FEE RATE (Cost Plus Fixed Fee — applied to all labor costs): | [5 empty] | Fee Rate: | 8% | ← Editable. Default = 8%. Changing updates ALL cost calculations automatically.
CLIN | Labor Category | Employee | Company | Burdened Rate ($/hr) | Updated Rates | Feb-Mar (M1) |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | Feb 1-23 |  | ANNUAL TOTAL
[6 empty] | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Hours | Cost+Fee ($) | Total Hrs | Total Cost+Fee ($)
CLIN 1006 — Software Maintenance
1006 | Software Engineer - Mid |  |  | 146.63 |  | 104 | 16469.4816 | 88 | 13935.7152 | 84 | 13302.2736 | 84 | 13302.2736 | 92 | 14569.1568 | 84 | 13302.2736 | 88 | 13935.7152 | 88 | 13935.7152 | 80 | 12668.832 | 88 | 13935.7152 | 80 | 12668.832 | 68 | 10768.5072 | 1028 | 162794.4912
1006 | Software Engineer - Mid |  |  | 128.32 |  | 0 | 0 | 88 | 12195.5328 | 84 | 11641.1904 | 84 | 11641.1904 | 92 | 12749.8752 | 84 | 11641.1904 | 88 | 12195.5328 | 88 | 12195.5328 | 80 | 11086.848 | 88 | 12195.5328 | 80 | 11086.848 | 68 | 9423.8208 | 924 | 128053.0944
1006 | Software Engineer - Mid |  |  | 131.57 |  | 104 | 14777.9424 | 88 | 11578.68 | 80 | 10525.68 | 88 | 11578.68 | 88 | 11578.68 | 84 | 11052.18 | 84 | 11052.18 | 88 | 11578.68 | 76 | 9999.72 | 80 | 10525.68 | 76 | 9999.72 | 68 | 8946.72 | 1004 | 133194.5424
1006 | Software Engineer - Senior |  |  | 159.18 |  | 104 | 17879.0976 | 88 | 15128.4672 | 84 | 14440.8096 | 84 | 14440.8096 | 92 | 15816.1248 | 84 | 14440.8096 | 88 | 15128.4672 | 88 | 15128.4672 | 80 | 13753.152 | 88 | 15128.4672 | 80 | 13753.152 | 68 | 11690.1792 | 1028 | 176728.0032
1006 | Software Engineer - Senior |  |  | 155.61 | 128.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1006 | Software Engineer - Senior |  |  | 166.81 |  | 104 | 18736.0992 | 88 | 14679.9 | 80 | 13345.02 | 88 | 14679.9 |  | 14679.9 |  | 14012.46 | 0 | 14012.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 104145.7392
1006 | Software Engineer - Senior |  |  | 89.63 |  | 104 | 10067.2416 | 88 | 7887.78 | 80 | 7170.66 | 88 | 7887.78 | 88 | 7887.78 | 84 | 7529.22 | 84 | 7529.22 | 88 | 7887.78 | 76 | 6812.1 | 80 | 7170.66 | 76 | 6812.1 | 68 | 6094.98 | 1004 | 90737.3016
1006 | Systems Engineer - Mid |  |  | 138.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1006 | Cybersecurity Engineer - Senior |  |  | 123.42 |  | 104 | 13862.5344 | 88 | 10861.02 | 80 | 9873.36 | 88 | 10861.02 | 88 | 10861.02 | 84 | 10367.46 | 84 | 10367.46 | 88 | 10861.02 | 76 | 9379.8 | 80 | 9873.36 | 76 | 9379.8 | 68 | 8392.68 | 1004 | 124940.5344
1006 | Test Engineer - Mid |  |  | 190 |  |  | 0 |  | 0 | 84 | 17236.8 | 84 | 17236.8 | 92 | 18878.4 | 84 | 17236.8 | 88 | 18057.6 | 88 | 18057.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 106704
1006 | TOTAL — CLIN 1006 |  |  |  |  | 624 | 91792.3968 | 616 | 86267.0952 | 656 | 97535.7936 | 688 | 101628.4536 | 632 | 107020.9368 | 588 | 99582.3936 | 604 | 102278.6352 | 616 | 89644.7952 | 468 | 63700.452 | 504 | 68829.4152 | 468 | 63700.452 | 408 | 55316.8872 | 6352 | 1027297.7064
CLIN 1007 — Software Development
1007 | Software Engineer - Mid |  |  | 146.63 |  | 104 | 16469.4816 | 88 | 13935.7152 | 84 | 13302.2736 | 84 | 13302.2736 | 92 | 14569.1568 | 84 | 13302.2736 | 88 | 13935.7152 | 88 | 13935.7152 | 80 | 12668.832 | 88 | 13935.7152 | 80 | 12668.832 | 68 | 10768.5072 | 1028 | 162794.4912
1007 | Software Engineer - Mid |  |  | 128.32 |  | 0 | 0 | 88 | 12195.5328 | 84 | 11641.1904 | 84 | 11641.1904 | 92 | 12749.8752 | 84 | 11641.1904 | 88 | 12195.5328 | 88 | 12195.5328 | 80 | 11086.848 | 88 | 12195.5328 | 80 | 11086.848 | 68 | 9423.8208 | 924 | 128053.0944
1007 | Software Engineer - Mid |  |  | 131.57 |  | 104 | 14777.9424 | 88 | 11578.68 | 80 | 10525.68 | 88 | 11578.68 | 88 | 11578.68 | 84 | 11052.18 | 84 | 11052.18 | 88 | 11578.68 | 76 | 9999.72 | 80 | 10525.68 | 76 | 9999.72 | 68 | 8946.72 | 1004 | 133194.5424
1007 | Software Engineer - Mid |  |  | 89.63 |  | 104 | 10067.2416 | 88 | 7887.78 | 80 | 7170.66 | 88 | 7887.78 | 88 | 7887.78 | 84 | 7529.22 | 84 | 7529.22 | 88 | 7887.78 | 76 | 6812.1 | 80 | 7170.66 | 76 | 6812.1 | 68 | 6094.98 | 1004 | 90737.3016
1007 | Software Engineer - Senior |  |  | 159.18 |  | 104 | 17879.0976 | 88 | 15128.4672 | 84 | 14440.8096 | 84 | 14440.8096 | 92 | 15816.1248 | 84 | 14440.8096 | 88 | 15128.4672 | 88 | 15128.4672 | 80 | 13753.152 | 88 | 15128.4672 | 80 | 13753.152 | 68 | 11690.1792 | 1028 | 176728.0032
1007 | Software Engineer - Senior |  |  | 155.61 | 128.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1007 | Software Engineer - Senior |  |  | 166.81 |  | 104 | 18736.0992 | 88 | 14679.9 | 80 | 13345.02 | 88 | 14679.9 |  | 14679.9 |  | 14012.46 | 0 | 14012.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 104145.7392
1007 | Systems Engineer - Mid |  |  | 138.49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1007 | Cybersecurity Engineer - Senior |  |  | 123.42 |  | 104 | 13862.5344 | 88 | 10861.02 | 80 | 9873.36 | 88 | 10861.02 | 88 | 10861.02 | 84 | 10367.46 | 84 | 10367.46 | 88 | 10861.02 | 76 | 9379.8 | 80 | 9873.36 | 76 | 9379.8 | 68 | 8392.68 | 1004 | 124940.5344
1007 | Test Engineer - Mid |  |  | 190 |  |  | 0 |  | 0 | 84 | 17236.8 | 84 | 17236.8 | 92 | 18878.4 | 84 | 17236.8 | 88 | 18057.6 | 88 | 18057.6 |  | 0 |  | 0 |  | 0 |  | 0 | 520 | 106704
1007 | TOTAL — CLIN 1007 |  |  |  |  | 624 | 91792.3968 | 616 | 86267.0952 | 656 | 97535.7936 | 688 | 101628.4536 | 632 | 107020.9368 | 588 | 99582.3936 | 604 | 102278.6352 | 616 | 89644.7952 | 468 | 63700.452 | 504 | 68829.4152 | 468 | 63700.452 | 408 | 55316.8872 | 6872 | 1027297.7064
CLIN 1008 — O&M
1008 | Database Specialist - Senior |  |  | 155.61 | 128.21 | 208 | 34956.2304 | 176 | 29578.3488 | 168 | 23262.4224 | 168 | 23262.4224 | 184 | 25477.8912 | 168 | 23262.4224 | 176 | 24370.1568 | 176 | 24370.1568 | 160 | 22154.688 | 176 | 24370.1568 | 160 | 22154.688 | 136 | 18831.4848 | 2056 | 296051.0688
1008 | Systems Engineer - Senior |  |  | 152.3487 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1008 | Systems/nit Engineer |  |  | 138.49 |  | 104 | 15555.1968 | 176 | 26324.1792 | 84 | 12563.8128 |  | 0 |  |  | \ | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 54443.1888
1008 | Cybersecurity Engineer - Senior |  |  | 123.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1008
1008 | TOTAL — CLIN 1008 | [5 empty] | 50511.4272 | 352 | 55902.528 | 252 | 35826.2352 | 168 | 23262.4224 | 184 | 25477.8912 | 168 | 23262.4224 | 176 | 24370.1568 | 176 | 24370.1568 | 160 | 22154.688 | 176 | 24370.1568 | 160 | 22154.688 | 136 | 18831.4848 | #VALUE! | 350494.2576

## 📅 Mar
Feb 24–Mar 31 — Monthly Burn Entry (Invoice Month 1)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP | 45545.44 | 0 | 45545.44 | 45545.44 | 0
1006 | Software Maintenance | CPFF | 139671.71 |  | 139671.71 | 91792.3968 | 47879.3132 | • Teammates not provided updated, equal split billing guidance. Therefore, BL teammates all billed 1006, and TH had a split between 1006 + 1007 • Waiss Q. was not forecasted to come back on paternity leave
1007 | Software Development | CPFF | 90434.31 |  | 90434.31 | 91792.3968 | -1358.0868
1008 | O&M | CPFF | 18521.33 | 0 | 18521.33 | 50511.4272 | -31990.0972
1009 | Tier 3 Helpdesk | FFP | 2590.77 | 0 | 2590.77 | 2590.77 | 0
1010 | Training | FFP | 15283.06 | 0 | 15283.06 | 15283.06 | 0
1016 | NTIA | FFP | 20596.19 | 0 | 20596.19 | 20596.19 | 0
1017 | Other Direct Costs | COST | 13845.75 | 0 | 13845.75 | 7000 | 6845.75
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 346488.56 | 0 | 346488.56 | 325111.6808 | 21376.8792
Detailed Summary of Total Variance
• 1006, 1007 - Q. not in Labor forecast for M1 due to earlier than planned return date from paternity leave; if we were to add his hours into the forecast, we would have had a 3k TOTAL variance (after accounting for the increased Crayon costs) instead of 21K • ODC - Crayon was only projected to be 7k but due to the part of Feb and March being combined the total was a little less than double the projected amount

## 📅 Apr
April — Monthly Burn Entry (M2)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.31 | -50425.31
1006 | Software Maintenance | CPFF |  | 0 | 0 | 86267.0952 | -86267.0952
1007 | Software Development | CPFF |  | 0 | 0 | 86267.0952 | -86267.0952
1008 | O&M | CPFF |  | 0 | 0 | 55902.528 | -55902.528
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.53 | -16920.53
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 97000 | -97000 | SQL (90k), Crayon (7k),
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 418453.8284 | -418453.8284

## 📅 May
May — Monthly Burn Entry (M3)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 48798.69 | -48798.69
1006 | Software Maintenance | CPFF |  | 0 | 0 | 97535.7936 | -97535.7936
1007 | Software Development | CPFF |  | 0 | 0 | 97535.7936 | -97535.7936
1008 | O&M | CPFF |  | 0 | 0 | 35826.2352 | -35826.2352
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2775.82 | -2775.82
1010 | Training | FFP |  | 0 | 0 | 16374.71 | -16374.71
1016 | NTIA | FFP |  | 0 | 0 | 22067.34 | -22067.34
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 327914.3824 | -327914.3824

## 📅 Jun
June — Monthly Burn Entry (M4)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.31 | -50425.31
1006 | Software Maintenance | CPFF |  |  | 0 | 101628.4536 | -101628.4536
1007 | Software Development | CPFF |  | 0 | 0 | 101628.4536 | -101628.4536
1008 | O&M | CPFF |  | 0 | 0 | 23262.4224 | -23262.4224
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.53 | -16920.53
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 326536.4396 | -326536.4396

## 📅 Jul
July — Monthly Burn Entry (M5)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 48798.69 | -48798.69
1006 | Software Maintenance | CPFF |  | 0 | 0 | 107020.9368 | -107020.9368
1007 | Software Development | CPFF |  | 0 | 0 | 107020.9368 | -107020.9368
1008 | O&M | CPFF |  | 0 | 0 | 25477.8912 | -25477.8912
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2775.82 | -2775.82
1010 | Training | FFP |  | 0 | 0 | 16374.71 | -16374.71
1016 | NTIA | FFP |  | 0 | 0 | 22067.34 | -22067.34
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 336536.3248 | -336536.3248

## 📅 Aug
August — Monthly Burn Entry (M6)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.31 | -50425.31
1006 | Software Maintenance | CPFF |  | 0 | 0 | 99582.3936 | -99582.3936
1007 | Software Development | CPFF |  | 0 | 0 | 99582.3936 | -99582.3936
1008 | O&M | CPFF |  | 0 | 0 | 23262.4224 | -23262.4224
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.53 | -16920.53
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 322444.3196 | -322444.3196

## 📅 Sep
September — Monthly Burn Entry (M7)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.31 | -50425.31
1006 | Software Maintenance | CPFF |  | 0 | 0 | 102278.6352 | -102278.6352
1007 | Software Development | CPFF |  | 0 | 0 | 102278.6352 | -102278.6352
1008 | O&M | CPFF |  | 0 | 0 | 24370.1568 | -24370.1568
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.53 | -16920.53
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 328944.5372 | -328944.5372

## 📅 Oct
October — Monthly Burn Entry (M8)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 48798.69 | -48798.69
1006 | Software Maintenance | CPFF |  | 0 | 0 | 89644.7952 | -89644.7952
1007 | Software Development | CPFF |  | 0 | 0 | 89644.7952 | -89644.7952
1008 | O&M | CPFF |  | 0 | 0 | 24370.1568 | -24370.1568
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2775.82 | -2775.82
1010 | Training | FFP |  | 0 | 0 | 16374.71 | -16374.71
1016 | NTIA | FFP |  | 0 | 0 | 22067.34 | -22067.34
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 300676.3072 | -300676.3072

## 📅 Nov
November — Monthly Burn Entry (M9)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.31 | -50425.31
1006 | Software Maintenance | CPFF |  | 0 | 0 | 63700.452 | -63700.452
1007 | Software Development | CPFF |  | 0 | 0 | 63700.452 | -63700.452
1008 | O&M | CPFF |  | 0 | 0 | 22154.688 | -22154.688
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.53 | -16920.53
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 249572.702 | -249572.702

## 📅 Dec
December — Monthly Burn Entry (M10)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 48798.69 | -48798.69
1006 | Software Maintenance | CPFF |  | 0 | 0 | 68829.4152 | -68829.4152
1007 | Software Development | CPFF |  | 0 | 0 | 68829.4152 | -68829.4152
1008 | O&M | CPFF |  | 0 | 0 | 24370.1568 | -24370.1568
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2775.82 | -2775.82
1010 | Training | FFP |  | 0 | 0 | 16374.71 | -16374.71
1016 | NTIA | FFP |  | 0 | 0 | 22067.34 | -22067.34
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 259045.5472 | -259045.5472

## 📅 Jan
January — Monthly Burn Entry (M11)
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.31 | -50425.31
1006 | Software Maintenance | CPFF |  | 0 | 0 | 63700.452 | -63700.452
1007 | Software Development | CPFF |  | 0 | 0 | 63700.452 | -63700.452
1008 | O&M | CPFF |  | 0 | 0 | 22154.688 | -22154.688
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.53 | -16920.53
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 249572.702 | -249572.702

## 📅 Feb-E
Feb (1st-23rd) — Monthly Burn Entry
Blue = enter data ¦ Gray = formula ¦ Green = cross-sheet link. Sub Actuals col locked for non-sub CLINs.
🟢 CPFF CLINs 1006/1007/1008 — Forecast auto-calculated from 💼 Labor Forecast tab. ¦ FFP/ODC CLINs 1005/1009/1010/1016/1017/1018 — enter Forecast directly in blue cells.
CLIN | Description | Type | Prime Actuals ($) | Sub Actuals ($) | Total Actuals ($) | Forecast ($) | Variance ($) | Notes
1005 | Project Management | FFP |  | 0 | 0 | 50425.3 | -50425.3
1006 | Software Maintenance | CPFF |  | 0 | 0 | 55316.8872 | -55316.8872
1007 | Software Development | CPFF |  | 0 | 0 | 55316.8872 | -55316.8872
1008 | O&M | CPFF |  | 0 | 0 | 18831.4848 | -18831.4848
1009 | Tier 3 Helpdesk | FFP |  | 0 | 0 | 2868.35 | -2868.35
1010 | Training | FFP |  | 0 | 0 | 16920.52 | -16920.52
1016 | NTIA | FFP |  | 0 | 0 | 22802.92 | -22802.92
1017 | Other Direct Costs | COST |  | 0 | 0 | 7000 | -7000
1018 | Travel | COST |  | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 229482.3492 | -229482.3492

## 📊 Burn Summary
BURN RATE SUMMARY — OPTION YEAR 1 OVERVIEW
All values auto-calculated. Do not manually edit this sheet.
Contract Ceiling |  | Total Funded |  | YTD Billed |  | YTD Forecast **NOT EAC** |  | Remaining Ceiling |  | Remaining Funding |  | % Burned vs Funded |  | % Funded vs Ceiling | Unfunded
3523254.67 |  | 2670173.32 |  | 346488.56 |  | 3674291.1204 |  | 3176766.11 |  | 2323684.76 |  | 12.98% |  | 75.79% | 853081.35
0
MONTHLY ACTUALS vs FORECAST vs CUMULATIVE BURN
Month | Prime Act | Sub Act | Total Act | Forecast | Variance | Cum Act | Cum Fore | Ceiling | Funded | Ceil Rem | Fund Rem | % Burn/Ceil | % Burn/Fund | Status
Feb-Mar (M1) | 346488.56 | 0 | 346488.56 | 325111.6808 | 21376.8792 | 346488.56 | 325111.6808 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
April | 0 | 0 | 0 | 418453.8284 | -418453.8284 | 346488.56 | 743565.5092 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
May | 0 | 0 | 0 | 327914.3824 | -327914.3824 | 346488.56 | 1071479.8916 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
June | 0 | 0 | 0 | 326536.4396 | -326536.4396 | 346488.56 | 1398016.3312 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
July | 0 | 0 | 0 | 336536.3248 | -336536.3248 | 346488.56 | 1734552.656 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
August | 0 | 0 | 0 | 322444.3196 | -322444.3196 | 346488.56 | 2056996.9756 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
September | 0 | 0 | 0 | 328944.5372 | -328944.5372 | 346488.56 | 2385941.5128 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
October | 0 | 0 | 0 | 300676.3072 | -300676.3072 | 346488.56 | 2686617.82 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
November | 0 | 0 | 0 | 249572.702 | -249572.702 | 346488.56 | 2936190.522 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
December | 0 | 0 | 0 | 259045.5472 | -259045.5472 | 346488.56 | 3195236.0692 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
January | 0 | 0 | 0 | 249572.702 | -249572.702 | 346488.56 | 3444808.7712 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
Feb (1st-23rd) | 0 | 0 | 0 | 229482.3492 | -229482.3492 | 346488.56 | 3674291.1204 | 3523254.67 | 2670173.32 | 3176766.11 | 2323684.76 | 9.834% | 12.98% | ✅ ON TRACK
TOTAL | 346488.56 | 0 | 346488.56 | 3674291.1204
CLIN-LEVEL ANNUAL BURN SUMMARY
CLIN | Description | Type | Ceiling ($) | Funded ($) | Total Billed | Rem Ceiling | Rem Funding | % Burn/Ceil | % Burn/Fund | Status | % Funded vs Ceiling | Status | Unfunded ($) (Ceiling − Funded)
1005 | Project Management | FFP | 593717.36 | 432918.91 | 45545.44 | 548171.92 | 387373.47 | 7.671% | 10.52% | ✅ ON TRACK | 72.92% | ✅ ON TRACK | 160798.45
1006 | Software Maintenance | CPFF | 727970.79 | 561144.15 | 139671.71 | 588299.08 | 421472.44 | 19.19% | 24.89% | ✅ ON TRACK | 77.08% | ✅ ON TRACK | 166826.64
1007 | Software Development | CPFF | 869923.61 | 670566.12 | 90434.31 | 779489.3 | 580131.81 | 10.4% | 13.49% | ✅ ON TRACK | 77.08% | ✅ ON TRACK | 199357.49
1008 | O&M | CPFF | 688014.82 | 501677.47 | 18521.33 | 669493.49 | 483156.14 | 2.692% | 3.692% | ✅ ON TRACK | 72.92% | ✅ ON TRACK | 186337.35
1009 | Tier 3 Helpdesk | FFP | 33772.5 | 24625.78 | 2590.77 | 31181.73 | 22035.01 | 7.671% | 10.52% | ✅ ON TRACK | 72.92% | ✅ ON TRACK | 9146.72
1010 | Training | FFP | 199225.6 | 145268.67 | 15283.06 | 183942.54 | 129985.61 | 7.671% | 10.52% | ✅ ON TRACK | 72.92% | ✅ ON TRACK | 53956.93
1016 | NTIA | FFP | 268485.99 | 268485.99 | 20596.19 | 247889.8 | 247889.8 | 7.671% | 7.671% | ✅ ON TRACK | 100% | ✅ ON TRACK | 0
1017 | Other Direct Costs | COST | 132000 | 60486.24 | 13845.75 | 118154.25 | 46640.49 | 10.49% | 22.89% | ✅ ON TRACK | 45.82% | ✅ ON TRACK | 71513.76
1018 | Travel | COST | 10144 | 4999.99 | 0 | 10144 | 4999.99 | 0% | 0% | ✅ ON TRACK | 49.29% | ✅ ON TRACK | 5144.01

## 📈 CLIN Charts
CLIN 1005 — Project Management (FFP)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 45545.44 | 45545.44 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Apr | 45545.44 | 95970.75 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
May | 45545.44 | 144769.44 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Jun | 45545.44 | 195194.75 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Jul | 45545.44 | 243993.44 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Aug | 45545.44 | 294418.75 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Sep | 45545.44 | 344844.06 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Oct | 45545.44 | 393642.75 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Nov | 45545.44 | 444068.06 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Dec | 45545.44 | 492866.75 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Jan | 45545.44 | 543292.06 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
Feb-E | 45545.44 | 593717.36 | 593717.36 | 432918.91 | 324689.1825 | 432918.91 | 432918.91
⚠️ Projected 75% Expenditure Month: |  | Sep
🔴 Projected 100% Expenditure Month: |  | Nov
CLIN 1006 — Software Maintenance (CPFF)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 139671.71 | 139671.71 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Apr | 139671.71 | 225938.8052 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
May | 139671.71 | 323474.5988 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Jun | 139671.71 | 425103.0524 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Jul | 139671.71 | 532123.9892 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Aug | 139671.71 | 631706.3828 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Sep | 139671.71 | 733985.018 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Oct | 139671.71 | 823629.8132 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Nov | 139671.71 | 887330.2652 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Dec | 139671.71 | 956159.6804 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Jan | 139671.71 | 1019860.1324 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
Feb-E | 139671.71 | 1075177.0196 | 727970.79 | 561144.15 | 420858.1125 | 561144.15 | 561144.15
⚠️ Projected 75% Expenditure Month: |  | Jun
🔴 Projected 100% Expenditure Month: |  | Aug
CLIN 1007 — Software Development (CPFF)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 90434.31 | 90434.31 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Apr | 90434.31 | 176701.4052 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
May | 90434.31 | 274237.1988 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Jun | 90434.31 | 375865.6524 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Jul | 90434.31 | 482886.5892 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Aug | 90434.31 | 582468.9828 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Sep | 90434.31 | 684747.618 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Oct | 90434.31 | 774392.4132 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Nov | 90434.31 | 838092.8652 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Dec | 90434.31 | 906922.2804 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Jan | 90434.31 | 970622.7324 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
Feb-E | 90434.31 | 1025939.6196 | 869923.61 | 670566.12 | 502924.59 | 670566.12 | 670566.12
⚠️ Projected 75% Expenditure Month: |  | Aug
🔴 Projected 100% Expenditure Month: |  | Sep
CLIN 1008 — O&M (CPFF)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 18521.33 | 18521.33 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Apr | 18521.33 | 74423.858 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
May | 18521.33 | 110250.0932 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Jun | 18521.33 | 133512.5156 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Jul | 18521.33 | 158990.4068 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Aug | 18521.33 | 182252.8292 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Sep | 18521.33 | 206622.986 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Oct | 18521.33 | 230993.1428 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Nov | 18521.33 | 253147.8308 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Dec | 18521.33 | 277517.9876 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Jan | 18521.33 | 299672.6756 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
Feb-E | 18521.33 | 318504.1604 | 688014.82 | 501677.47 | 376258.1025 | 501677.47 | 501677.47
⚠️ Projected 75% Expenditure Month: |  | Not yet projected
🔴 Projected 100% Expenditure Month: |  | Not yet projected
CLIN 1009 — Tier 3 Helpdesk (FFP)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 2590.77 | 2590.77 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Apr | 2590.77 | 5459.12 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
May | 2590.77 | 8234.94 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Jun | 2590.77 | 11103.29 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Jul | 2590.77 | 13879.11 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Aug | 2590.77 | 16747.46 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Sep | 2590.77 | 19615.81 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Oct | 2590.77 | 22391.63 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Nov | 2590.77 | 25259.98 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Dec | 2590.77 | 28035.8 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Jan | 2590.77 | 30904.15 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
Feb-E | 2590.77 | 33772.5 | 33772.5 | 24625.78 | 18469.335 | 24625.78 | 24625.78
⚠️ Projected 75% Expenditure Month: |  | Sep
🔴 Projected 100% Expenditure Month: |  | Nov
CLIN 1010 — Training (FFP)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 15283.06 | 15283.06 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Apr | 15283.06 | 32203.59 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
May | 15283.06 | 48578.3 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Jun | 15283.06 | 65498.83 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Jul | 15283.06 | 81873.54 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Aug | 15283.06 | 98794.07 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Sep | 15283.06 | 115714.6 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Oct | 15283.06 | 132089.31 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Nov | 15283.06 | 149009.84 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Dec | 15283.06 | 165384.55 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Jan | 15283.06 | 182305.08 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
Feb-E | 15283.06 | 199225.6 | 199225.6 | 145268.67 | 108951.5025 | 145268.67 | 145268.67
⚠️ Projected 75% Expenditure Month: |  | Sep
🔴 Projected 100% Expenditure Month: |  | Nov
CLIN 1016 — NTIA (FFP)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 20596.19 | 20596.19 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Apr | 20596.19 | 43399.11 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
May | 20596.19 | 65466.45 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Jun | 20596.19 | 88269.37 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Jul | 20596.19 | 110336.71 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Aug | 20596.19 | 133139.63 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Sep | 20596.19 | 155942.55 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Oct | 20596.19 | 178009.89 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Nov | 20596.19 | 200812.81 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Dec | 20596.19 | 222880.15 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Jan | 20596.19 | 245683.07 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
Feb-E | 20596.19 | 268485.99 | 268485.99 | 268485.99 | 201364.4925 | 268485.99 | 268485.99
⚠️ Projected 75% Expenditure Month: |  | Dec
🔴 Projected 100% Expenditure Month: |  | Feb-E
CLIN 1017 — ODCs (COST)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar | 13845.75 | 13845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Apr | 13845.75 | 110845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
May | 13845.75 | 117845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Jun | 13845.75 | 124845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Jul | 13845.75 | 131845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Aug | 13845.75 | 138845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Sep | 13845.75 | 145845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Oct | 13845.75 | 152845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Nov | 13845.75 | 159845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Dec | 13845.75 | 166845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Jan | 13845.75 | 173845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
Feb-E | 13845.75 | 180845.75 | 132000 | 60486.24 | 45364.68 | 60486.24 | 60486.24
⚠️ Projected 75% Expenditure Month: |  | Apr
🔴 Projected 100% Expenditure Month: |  | Apr
CLIN 1018 — Travel (COST)
Month | Cum Actuals (WAWF) | EAC: Act + Remaining Forecast | Ceiling ($) | Funded ($) | 75% Threshold | 100% Threshold | 100% Threshold ($)
Feb-Mar |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Apr |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
May |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Jun |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Jul |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Aug |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Sep |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Oct |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Nov |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Dec |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Jan |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
Feb-E |  | 0 | 10144 | 4999.99 | 3749.9925 | 4999.99 | 4999.99
⚠️ Projected 75% Expenditure Month: |  | Not yet projected
🔴 Projected 100% Expenditure Month: |  | Not yet projected

## 📊 Overall Chart
OVERALL CONTRACT BURN — Monthly Actual vs Forecast & Cumulative EAC
Month | Monthly Actual ($) | Monthly Forecast ($) | Cum Actuals (WAWF) | EAC: Act + Rem. Forecast | Ceiling ($) | Funded ($)
Mar | 346488.56 | 325111.6808 | 346488.56 | 346488.56 | 3523254.67 | 2670173.32
Apr | 0 | 418453.8284 | 346488.56 | 764942.3884 | 3523254.67 | 2670173.32
May | 0 | 327914.3824 | 346488.56 | 1092856.7708 | 3523254.67 | 2670173.32
Jun | 0 | 326536.4396 | 346488.56 | 1419393.2104 | 3523254.67 | 2670173.32
Jul | 0 | 336536.3248 | 346488.56 | 1755929.5352 | 3523254.67 | 2670173.32
Aug | 0 | 322444.3196 | 346488.56 | 2078373.8548 | 3523254.67 | 2670173.32
Sep | 0 | 328944.5372 | 346488.56 | 2407318.392 | 3523254.67 | 2670173.32
Oct | 0 | 300676.3072 | 346488.56 | 2707994.6992 | 3523254.67 | 2670173.32
Nov | 0 | 249572.702 | 346488.56 | 2957567.4012 | 3523254.67 | 2670173.32
Dec | 0 | 259045.5472 | 346488.56 | 3216612.9484 | 3523254.67 | 2670173.32
Jan | 0 | 249572.702 | 346488.56 | 3466185.6504 | 3523254.67 | 2670173.32
Feb-E | 0 | 229482.3492 | 346488.56 | 3695667.9996 | 3523254.67 | 2670173.32
|  | Projected Contract Overage (Variance) |  | 172413.3296 | % amount
450000
|  |  | Amt avail to spend | 277586.6704