## Instructions
CHANGE LOG — INSTRUCTIONS & FIELD DEFINITIONS
v2.0 Program • Owner: Program Management • All contract changes must be logged at point of occurrence
FIELD | DEFINITION | ACCEPTED VALUES / GUIDANCE
Change ID | Unique identifier. Format: CR-XXX (e.g., CR-001). Never reuse. | CR-001, CR-002 …
Date Submitted | Date the change was first formally identified or requested. | MM/DD/YYYY
Date Approved/Rejected | Date a decision was made on this change request. | MM/DD/YYYY or Pending
Change Title | Short descriptive title (≤10 words). | Free text
Change Description | Full narrative of what is changing and why it is necessary. | Be specific — include root cause and triggering event
Change Type | Classification of the change. | Scope / Schedule / Cost / Technical / Contractual / Personnel / Process
Initiated By | Who identified or requested the change. | Government Customer / PM / Tech Lead / Security Lead / Contracting Officer / Other
Branch Impacted | Which functional branch(es) does this change affect. | One or more of the six branches
Cost Impact ($) | Estimated dollar impact. Use 0 if none. Negative = savings. | Dollar value — positive = cost increase
Schedule Impact (days) | Number of calendar days the program schedule is affected. 0 if none. | Integer — positive = delay, negative = acceleration
Scope Impact | Narrative description of how program scope is affected, if at all. | Free text or 'None'
Decision Authority | Who has authority to approve this change. | PM / Corporate Leadership / Contracting Officer / Government COR / Government CO
Status | Current disposition of the change request. | Pending / Approved / Rejected / On Hold / Implemented
Approved By | Name and title of person who formally approved or rejected. | Full name + title
Contract Mod Required | Does this change require a formal contract modification? | Yes / No / Under Review
Mod Number | If a contract modification was executed, record the mod number here. | MOD-001 format or N/A
Implementation Date | Date the change was or will be implemented. | MM/DD/YYYY or TBD
Related Risk ID | If this change was triggered by or creates a risk, link to the Risk Register. | R-001 format or N/A
Notes | Additional context, decisions, links to supporting documentation. | Free text

## Change Log
PROGRAM CHANGE LOG
v2.0 Program • Owner: Program Management • Log changes at point of occurrence — do not batch
Change ID | Date Submitted | Date Approved/ Rejected | Change Title | Change Description | Change Type | Initiated By | Branch Impacted | Cost Impact ($) | Schedule Impact (days) | Scope Impact | Decision Authority | Status | Approved By | Contract Mod Required | Mod Number | Implementation Date | Related Risk ID | Notes
CR-001 | 06/01/2026 | 06/10/2026 | Scope Addition: Mobile Responsive UI | Government customer requested mobile-responsive interface for field users. Not included in original SOW. Requires additional front-end development effort. | Scope | Government Customer | 2.0 Software Development | 45000 | 21 | Addition of mobile UI layer across all existing features. Estimated 3-sprint effort. | Contracting Officer | Approved | Jane Smith, CO | Yes | MOD-001 | 08/15/2026 | R-002 | MOD-001 executed 06/10. Sprint planning updated.
CR-002 | 06/08/2026 | Pending | ATO Timeline Extension Request | STIG remediation findings are taking longer than planned. Requesting 30-day extension to ATO submission deadline to ensure complete remediation. | Schedule | Security Lead | 3.0 Security & Compliance | 0 | 30 | No scope change. Schedule impact only on ATO submission milestone. | Government COR | Pending | — | No | N/A | TBD | R-001 | Submitted to COR 06/08. Awaiting response.
CR-003 | 06/15/2026 | 06/18/2026 | Personnel Change: Replace 1099 Dev SME | Senior developer transitioning off contract. Replacement identified. Knowledge transfer period required before full productivity. | Personnel | PM | 2.0 Software Development | 8000 | 14 | No scope change. Temporary velocity reduction during knowledge transfer. | PM | Approved | Bri [PM], Program Lead | No | N/A | 07/01/2026 | R-004 | KT sessions scheduled 06/20–07/01. New resource onboarded.
CR-004 | 06/20/2026 | Pending | GFE Procurement Path Change | Original GFE procurement path is blocked. Government exploring alternate equipment source. May require environment reconfiguration. | Technical | Government Customer | 4.0 Infra & Environment | 12000 | 45 | Potential reconfiguration of dev/test/prod environment if alternate GFE has different specs. | Government COR | Pending | — | Under Review | N/A | TBD | R-003 | Infra lead assessing alternate GFE specs. Decision expected 07/01.

## Change Summary
CHANGE LOG SUMMARY DASHBOARD
Auto-calculated from Change Log tab • Do not edit this sheet directly
CHANGES BY STATUS
Status | Count | Total Cost Impact ($) | Total Schedule Impact (days)
Approved | 2 | 53000 | 35
Pending | 2 | 12000 | 75
Rejected | 0 | 0 | 0
On Hold | 0 | 0 | 0
Implemented | 0 | 0 | 0
TOTAL | 4 | 65000 | 110
CHANGES BY TYPE
Change Type | Count | Total Cost Impact ($) | Contract Mod Required
Scope | 1 | 45000 | 1
Schedule | 1 | 0 | 0
Cost | 0 | 0 | 0
Technical | 1 | 12000 | 0
Contractual | 0 | 0 | 0
Personnel | 1 | 8000 | 0
Process | 0 | 0 | 0